## 工作表1
CS401 Project Task Division and Scheduling
November 20, 2020 - November 30, 2020
Participant： Wei Wu , Ye Yu
NO. | Task description | Time（days） | People in charge | Nov,2020
|  |  |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Analyze project requirements | 1 | Wei Wu , Ye Yu | bar: Nov,2020 20
2 | Create project engineering and work task division | 1 | Wei Wu , Ye Yu
3 | Design UML diagram for data structure | 1 | Wei Wu | bar: Nov,2020 21
4 | Design user operation flow chart | 1 | Wei Wu | bar: Nov,2020 21
5 | Coding ListInterface.class and BSTInterface.class | 1 | Wei Wu | bar: Nov,2020 22
6 | Coding ArrayBoundedListImplclass and ArrayUnBoundedListImpl.class | 1 | Wei Wu
7 | Coding ArrayBoundedListSortedImpl.class and ArrayUnBoundedListSortedImpl.class | 1 | Wei Wu | bar: Nov,2020 23
8 | Coding ArrayBoundedListSortedLineImpl.class and ArrayUnBoundedListSortedLineImpl.class | 1 | Wei Wu
9 | Coding BinarySearchTree.class | 1 | Wei Wu | bar: Nov,2020 24
10 | Test data structure class and modify bug | 1 | Wei Wu | bar: Nov,2020 24
11 | Coding LinkedBoundedListImpl.class and LinkedUnBoundedListImpl.class | 1 | Ye Yu | bar: Nov,2020 22
12 | Coding LinkedBoundedListSortedImpl.class and LinkedUnBoundedListSortedImpl.class | 1 | Ye Yu | bar: Nov,2020 23
13 | Coding LinkedBoundedListSortedBinaryImpl.class and LinkedUnBoundedListSortedBinaryImpl.class | 1 | Ye Yu | bar: Nov,2020 24
14 | Test data structure class and modify bug | 1 | Ye Yu | bar: Nov,2020 24
15 | Develop window program | 3 | Wei Wu,Ye Yu | bar: Nov,2020 25 to Nov,2020 27
16 | Write user manual | 1 | Wei Wu,Ye Yu | bar: Nov,2020 28
17
18
19
20